## Start here
Project tracker and Gantt practice workbook
Type your own formula in each yellow cell. The Check column tells you when it matches the green answer.
Plan - each task's end date (start + duration - 1) and its status on the status date in cell K1.
Gantt - the bars are conditional formatting: a day is shaded when it falls between a task's start and end.
The tutorial: https://www.datahubpro.co.uk/tutorials/project-tracker-excel
Want this on your own spreadsheet? Upload it at https://www.datahubpro.co.uk/try (free, no sign-up)
Made with DataHub Pro

## Plan
Task | Start | Days | % done | Your turn: End | Check | Answer (live formula) | Your turn: Status | Check | Answer (live formula) | Status date | 2027-03-12
Scope and plan | 2027-03-01 | 3 | 100%
Data collection | 2027-03-04 | 5 | 100%
Build dashboard | 2027-03-08 | 6 | 60%
Review with finance | 2027-03-11 | 2 | 0%
Board report | 2027-03-15 | 3 | 0%

## Gantt
Task | 2027-03-01 | 2027-03-02 | 2027-03-03 | 2027-03-04 | 2027-03-05 | 2027-03-06 | 2027-03-07 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19
Change a start date or duration on Plan and the bars move.