## Instructions
Project Tracker Template
Free template by DataHub Pro · datahubpro.co.uk · hello@datahubpro.co.uk
A self-updating project tracker: enter tasks with owners and due dates, pick a status, and the tracker calculates days left, a RAG flag and overall completion automatically. Sample data is included — clear it and add your own.
How to use it
• Add one row per task on the Tasks sheet: Task, Owner, Start, Due, Status, % Complete.
• Pick Status from the dropdown (Not started / In progress / Blocked / Done).
• Days Left and RAG Status calculate themselves; overdue rows turn red, due-soon amber.
• The Dashboard sheet rolls up totals and overall % complete — no editing needed.
• Everything uses plain formulas: no macros, no add-ins, works in Excel 2016+ and 365.
If you found this useful, the full DataHub Pro platform does this on every spreadsheet you upload — try it free at datahubpro.co.uk/try
▶ Build this automatically from your own file — https://www.datahubpro.co.uk/try

## Tasks
Task | Owner | Start Date | Due Date | Status | % Complete | Days Left | RAG Status
Kick-off & scope | Ava | 2026-06-21 | 2026-06-28 | Done | 100%
Requirements doc | Ben | 2026-06-25 | 2026-07-03 | Done | 100%
Design mockups | Cara | 2026-06-29 | 2026-07-07 | In progress | 60%
Backend API | Dan | 2026-07-02 | 2026-07-14 | In progress | 35%
Frontend build | Ava | 2026-07-05 | 2026-07-19 | Not started | 0%
Data migration | Ben | 2026-07-07 | 2026-07-11 | Blocked | 10%
QA & testing | Cara | 2026-07-15 | 2026-07-25 | Not started | 0%
Security review | Dan | 2026-07-17 | 2026-07-21 | Not started | 0%
Docs & training | Ava | 2026-07-20 | 2026-07-27 | Not started | 0%
Launch | Team | 2026-07-27 | 2026-07-30 | Not started | 0%
Formulas:
Days Left = IF([Status]="Done","",[Due Date]-TODAY())

## Dashboard
Project Dashboard
Total tasks
Completed
In progress
Blocked
Overdue (not done)
Overall % complete